## Sheet1
ATLAS IMMUNIZATION
PATIENT MODULE
No. of Pages | Pages | STATUS
1 | 01a_Login | Completed
2 | 01b_Forgot Password | Completed
3 | 02_Register | Completed
4 | 03Aa_School-TB&OTherVaccines1 | Completed
5 | 03Ab_Booking-Confirmation_TB$OV | Completed
6 | 03Ac_School-TB&OTherVaccines2 | Completed
7 | 03Ba_Booking-School_Vaccines1 | Completed
8 | 03Bb_School-Confirmation_Specify Vaccines Only | Completed
9 | 03Bc_Booking-School_Vaccines2 | Completed
10 | 03Ca_Booking-School_TBTest1 | Completed
11 | 03Cb_School-Confirmation_TB Test Only | Completed
12 | 03Cc_Booking-School_TBTest2 | Completed
13 | 04Aa_Work-TB&OTherVaccines1 | Completed
14 | 04Ab_Work-Confirmation_TB$OV | Completed
15 | 04Ac_Work-TB&OTherVaccines2 | Completed
16 | 04Ba_Work-School_Vaccines1 | Completed
17 | 04Bb_Work-Confirmation_Specify Vaccines Only | Completed
18 | 04Bc_Work_Vaccines2 | Completed
19 | 04Ca_Work_TBTest1 | Completed
20 | 04Cb_Work-Confirmation_TB Test Only | Completed
21 | 04Cc_Work_TBTest2 | Completed
22 | 05Aa_Travel_New-Trip | Completed
23 | 05Ab_Travel-Confirmation-Details | Completed
24 | 05Ac_Travel_New-Trip-Form | Completed
25 | 05Ba_Travel_Followup-Date and Time | Completed
26 | 05Bb_Travel_Followup-Confirmation | Completed
27 | 05Bc_Travel_Followup-Form | Completed
28 | 06Aa_Followup-Booster_Date and Time | Completed
29 | 06Ab_Followup-Booster_Confirmation | Completed
30 | 06Ac_Followup-Booster_Form | Completed
31 | 07Aa_Doctor-Consult_1 | Completed
32 | 07Ab_Doctor-Consult_Confirmation | Completed
33 | 07Ac_Doctor-Consult_Form | Completed
34 | 08a_Booked-Appointments | Completed
35 | 08b_Appointment-Detail_School | Completed
36 | 08c_Appointment-Detail_School | Completed
37 | 08d_Appointment-Detail_School | Completed
38 | 08e_Appointment-Detail_Travel | Completed
39 | 08f_Appointment-Detail_Travel | Completed
40 | 08g_Appointment-Detail_Followup | Completed
41 | 08h_Doctor-Consult_Form_View | Completed
42 | 09Aa_Invoice-History | Completed
43 | 09Ab_Invoice-History_Invoice | Completed
44 | 10A_Profile-Update | Completed
45 | Delete-Popup_Confirmation | Completed
46 | Notification-Popup_Confirmation | Completed
NURSE MODULE
No. of Pages | Pages | STATUS | Hours | Date
1 | 01a_Login |  | 3 | 2020-10-08
2 | 01b_Forgot Password |  | 3 | 2020-10-08
3 | 02_Today's_Appointments |  | 6 | 2020-10-08
4 | 03Aa_School-TBPlus OtherVaccines_View-Popup |  | 8 | 2020-10-08
5 | 03Ab_School-VaccinesOnly_View-Popup |  | 4 | 2020-10-08
6 | 03Ab_School-TBTestOnly_View-Popup |  | 6 | 08/09-10-2020
7 | 03Ba_Travel-NewTrip_View-Popup |  | 7 | 2020-10-09
8 | 03Bb_TravelFollowup_View-Popup |  | 6 | 2020-10-09
9 | 03C_Followup_View-Popup |  | 7 | 2020-10-09
10 | 03D_Doctor Consult-Popup |  | 9 | 09/12-10-2020
11 | 04B_Vaccine_Detail_Popup |  | 4 | 2020-10-12
12 | 06Aa_Upcoming_Appointments |  | 5 | 2020-10-12
13 | 03Ba_Travel-NewTrip_View-Popup |  | 9 | 2020-10-12
14 | 03Bb_Travel-NewTrip_Patient1 |  | 5 | 12/13-10-2020
15 | 03Bc_Travel-NewTrip_Patient2 |  | 4 | 2020-10-13
16 | 04Aa_School-Form_Edit |  | 9 | 2020-10-13
17 | 04Ab_School-VaccinesOnly_Edit |  | 5 | 2020-10-13
18 | 04Ac_School-TBTestOnly_Edit |  | 4 | 2020-10-13
19 | 05Aa_Travel-Form_Edit |  | 4 | 2020-10-14
20 | 05Ab_New-Win_Travel_Edit_Patient1 |  | 5 | 2020-10-14
21 | 05Ac_New-Win_Travel_Edit_Patient2 |  | 6 | 2020-10-14
22 | 05Ba_New-Win_TravelFollowup_Edit |  | 5 | 2020-10-14
23 | 06Aa_New-Win_Followup_Edit |  | 5 | 2020-10-14
24 | 07A_Doctor Consult_Edit_Patient1 |  | 10 | 14/15-10-2020
25 | 07_Profile-Update |  | 5 | 2020-10-15
26 | 09_Notification |  | 5 | 2020-10-15
27 | 08_Profile_Drop_Down |  | 1 | 2020-10-15
28 | Status Update - Confirmation Popup | completed | 5 | 2020-10-15
29 | Status Update - Confirmation Popup | completed | 3 | 2020-10-15
30 | Messaging |  | 4 | 2020-10-16
RECEPTIONIST MODULE
No. of Pages | Pages | STATUS | Hours | Date
1 | 01a_Login | Completed |  | 2020-10-16
2 | 01b_Forgot Password | Completed |  | 2020-10-16
3 | 03_Dashboard |  | 10 | 2020-10-16
4 | Delete-Popup_Confirmation | Completed |  | 2020-10-16
5 | 04Aa_Booking-Immunization_School | Completed |  | 2020-10-16
6 | 04Ab_Booking-Immunization_School | Completed |  | 2020-10-16
7 | 04Ba_Booking-Immunization_School | Completed |  | 2020-10-19
8 | 04Bb_Booking-Immunization_School | Completed |  | 2020-10-19
9 | 04Ca_Booking-Immunization_School | Completed |  | 2020-10-19
10 | 04Cc_Booking-Immunization_School | Completed |  | 2020-10-19
11 | 05Aa_Work-TB&OTherVaccines1 | Completed |  | 2020-10-19
12 | 05Ab_Booking-Immunization_Work | Completed |  | 2020-10-19
13 | 05Ba_Work-School_Vaccines1 | Completed |  | 2020-10-20
14 | 05Bb_Booking-Immunization_Work | Completed |  | 2020-10-20
15 | 05Ca_Work_TBTest1 | Completed |  | 2020-10-20
16 | 05Cb_Booking-Immunization_Work | Completed |  | 2020-10-20
17 | 06Aa_Immunization_Travel-New Trip | Completed |  | 2020-10-20
18 | 06Ab_Booking-Immunization_Travel | Completed |  | 2020-10-20
19 | 06Ba_Immunization_Travel-New Trip | Completed |  | 2020-10-21
20 | 06Bb_Booking-Immunization_Travel | Completed |  | 2020-10-21
21 | 07Aa_Immunization_Follow-up_Booster | Completed |  | 2020-10-21
22 | 07Ab_Booking-Immunization_FollowBooster | Completed |  | 2020-10-21
23 | 08Aa_Medical_Doctor Consult | Completed |  | 2020-10-21
24 | 08Ab_Booking-Doctor Consult | Completed |  | 21/22-10-2020
25 | 09Aa_Booking-Corporates | Completed |  | 2020-10-22
26 | 09Ab_Booking-Corporate Booking | Completed |  | 2020-10-22
27 | 10Aa_Appointments-Requested | Completed
28 | Cancel Appointment-Popup_Confirmation | Completed
29 | Declined - Reason Popup | Completed
30 | 10Ab_Appointments-Requested | Completed |  | 2020-10-22
31 | 10Ac_Appointments-Requested | Completed |  | 22/23-10-2020
32 | 10Ad_Appointments-Requested | Completed |  | 2020-10-23
33 | 10Ba_Appointments-Rejected | Completed
34 | 10Bb_Appointments-Rejected | Completed |  | 2020-10-23
35 | 10Bc_Appointments-Rejected | Completed |  | 2020-10-23
36 | 10Bd_Appointments-Rejected | Completed |  | 2020-10-23
37 | 10Ca_Users Online List | Completed |  | 2020-10-26
38 | 10Cb_Appointments-Requested | Completed |  | 2020-10-26
39 | 10Cc_Appointments-Requested | Completed |  | 2020-10-26
40 | 10Cd_Appointments-Requested | Completed |  | 2020-10-26
41 | 10Ce_Appointments-Requested | Completed | 6 | 2020-10-26
42 | 10Da_Completed Appointments | Completed
43 | 10Db_Completed Appointments |  | 5 | 2020-10-27
44 | 10Dc_Completed Appointments |  | 5 | 2020-10-27
45 | 10Dd_Completed Appointments |  | 8 | 2020-10-27
46 | 11Aa_Corporate Appointments | Completed | 3 | 2020-10-27
47 | Invoice Popup |  | 4 | 2020-10-27
48 | Frame 13 | Completed
49 | 11Ab_Corporate Appointments - Detail | Completed | 5 | 27/28-10-2020
50 | 11Ba_Corporate Appointments | Completed | 3 | 2020-10-28
51 | 11Bb_Corporate Appointments - Detail | Completed | 6 | 2020-10-28
52 | 11Ca_Corporate Appointments | Completed | 3 | 2020-10-28
53 | 11Cb_Corporate Appointments | Completed | 5 | 2020-10-28
54 | 12Aa_Todays Appointment |  | 4 | 2020-10-28
55 | 12Ab_Todays Appointment_Followup booster |  | 5 | 28/29-10-2020
56 | 12Ab_Todays Appointment_Followup booster |  | 7 | 2020-10-29
57 | 12Ab_Todays Appointment_Followup booster |  | 5 | 2020-10-29
58 | 12Ba_Todays Appointment_Travel |  | 7 | 2020-10-29
59 | 12Bb_Todays Appointment_Travel Edit1 |  | 5 | 2020-10-29
60 | 12Bc_Todays Appointment_Travel Edit2 |  | 7 | 2020-10-30
61 | 12Bd_Todays Appointment_Travel Edit3 |  | 5 | 2020-10-30
62 | 12Ca_Todays Appointment_Followup booster |  | 6 | 2020-10-30
63 | 12Cb_Todays Appointment_Followup booster |  | 5 | 2020-10-30
64 | 12Da_Doctor Consult_View |  | 8 | 30-10-2020/02-11-20
65 | 12Db_Doctor Consult_Edit_Patient1 |  | 8 | 2020-11-02
66 | 13Aa_National_Network | Completed | 3 | 2020-11-02
67 | 13Ab_National_Network_Add_Company | Completed | 4 | 2020-11-02
68 | 13Ab_National_Network_Add_Company | Completed | 4 | 2020-11-02
69 | 13Ae_National_Network_Employee_View | Completed | 5 | 2020-11-02
70 | 13Ac_National_Network_Company_Deta | Completed | 5 | 2020-11-03
71 | 13Ac_National_Network_Company_Deta | Completed | 5 | 2020-11-03
72 | 13Ba_National_Network - Reports | Completed | 4 | 2020-11-03
73 | 14Aa_Corporate - Manage Users | Completed | 2 | 2020-11-03
74 | 14Ab_Users Add Edit | Completed | 5 | 2020-11-03
75 | 14Ac_Users Detail | Completed | 3 | 2020-11-03
76 | 14Ba_Corporate - Invoice | Completed | 3 | 2020-11-03
77 | 14Bb_Invoice - Detail | Completed | 4 | 2020-11-04
78 | 14Ca_Corporate - Reports | Completed | 3 | 2020-11-04
79 | 15a_Prepaid Users | Completed | 3 | 2020-11-04
80 | 16a_Manage Invoice | Completed | 2 | 2020-11-04
81 | 16b_Invoice detail | Completed | 3 | 2020-11-04
82 | 17_Manage Profile | Completed | 4 | 2020-11-04
83 | Declined - Reason Popup | Completed
SUPER ADMIN MODULE
No. of Pages | Pages | STATUS | Hours | Date
1 | 01a_Login |  | 3 | 2020-11-04
2 | 01b_Forgot Password |  | 3 | 2020-11-04
3 | 02_Dashboard |  | 6 | 2020-11-05
4 | 03_My-Profile |  | 8 | 2020-11-05
5 | Delete-Popup_Confirmation |  | 4 | 2020-11-05
6 | Cancel Appointment-Popup_Confirmation |  | 6 | 2020-11-05
7 | Rejected - Reason Popup |  | 7 | 05/06-11-2020
8 | Frame 10 |  | 6 | 2020-11-06
9 | 04AA_Appointments-Requested |  | 7 | 2020-11-06
10 | 04AB_Appointments-Requested |  | 9 | 2020-11-06
11 | 04AC_Appointments-Requested |  | 4 | 2020-11-09
12 | 04AD_Appointments-Requested |  | 5 | 2020-11-09
13 | 04BA_Appointments-Rejected |  | 9 | 2020-11-09
14 | 04BB_Appointments-Requested |  | 5 | 2020-11-09
15 | 04BC_Appointments-Requested |  | 4 | 2020-11-09
16 | 04BD_Appointments-Requested |  | 9 | 2020-11-10
17 | 04CA_Users Online List |  | 5 | 2020-11-10
18 | 04CB_Appointments-Requested |  | 4 | 2020-11-10
19 | 04CC_Appointments-Requested |  | 4 | 2020-11-10
20 | 04CD_Appointments-Requested |  | 5 | 2020-11-10
21 | 04CE_Appointments-Requested |  | 6 | 2020-11-11
22 | 04DA_Completed Appointments |  | 5 | 2020-11-11
23 | 04DB_Completed Appointments - Detail |  | 5 | 2020-11-11
24 | 04DC_Completed Appointments - Detail |  | 10 | 2020-11-11
25 | 04DD_Completed Appointments - Detail |  | 5 | 2020-11-12
26 | 04DE_Completed Appointments - Detail |  | 5 | 2020-11-12
27 | Invoice Popup |  | 1 | 2020-11-12
28 | Frame 13 |  | 5 | 2020-11-12
29 | 05Aa_Corporate Appointments |  | 3 | 2020-11-12
30 | 05Ab_Corporate Appointments - Detail |  | 4 | 2020-11-12
31 | 05Aa_Corporate Appointments |  | 3 | 2020-11-12
32 | 05Ab_Corporate Appointments - Detail |  | 6 | 2020-11-13
33 | 05Aa_Corporate Appointments |  | 2 | 2020-11-13
34 | 05Ab_Corporate Appointments - Detail |  | 4 | 2020-11-13
35 | 06Aa_Todays Appointment |  | 4 | 2020-11-13
36 | 06Ab_Todays Appointment_School View |  | 5 | 2020-11-13
37 | 06Ac_Todays Appointment_School Edit |  | 8 | 13/19-11-2020
38 | 06Ba_Todays Appointment_TravelView |  | 6 | 2020-11-19
39 | 06Bb_Todays Appointment_TravelEdit1 |  | 4 | 2020-11-19
40 | 06Bc_Todays Appointment_TravelEdit2 |  | 5 | 2020-11-19
41 | 06Bd_Todays Appointment_TravelEdit3 |  | 5 | 2020-11-19
42 | 06Ca_Todays Appointment_Followup booster |  | 4 | 2020-11-19
43 | 06Cb_Todays Appointment_Followup booster |  | 5 | 2020-11-20
44 | 06Da_Doctor Consult_View |  | 8 | 2020-11-20
45 | 06Db_Doctor Consult_Edit_Patient1 |  | 9 | 2020-11-20
46 | 07Aa_Booking-Immunization_School |  | 5 | 2020-11-20
47 | 07Aa_Booking-Immunization_School |  | 1 | 2020-11-23
48 | 07Ab_Booking-Immunization_School |  | 2 | 2020-11-23
49 | 07Aa_Booking-Immunization_School |  | 1 | 2020-11-23
50 | 07Ac_Booking-Immunization_School |  | 2 | 2020-11-23
51 | 07Aa_Booking-Immunization_School |  | 1 | 2020-11-23
52 | 07Ba_Work-TB&OTherVaccines1 |  | 2 | 2020-11-23
53 | 07Aa_Booking-Immunization_School |  | 1 | 2020-11-23
54 | 07Bb_Work-School_Vaccines1 |  | 2 | 2020-11-23
55 | 07Aa_Booking-Immunization_School |  | 1 | 2020-11-23
56 | 07Bc_Work_TBTest1 |  | 2 | 2020-11-23
57 | 07Aa_Booking-Immunization_School |  | 1 | 2020-11-23
58 | 07Ca_Immunization_Travel-New Trip |  | 3 | 2020-11-23
59 | 07Aa_Booking-Immunization_School |  | 1 | 2020-11-23
60 | 07Cb_Immunization_Travel-New Trip |  | 2 | 2020-11-23
61 | 07Aa_Booking-Immunization_School |  | 1 | 2020-11-23
62 | 07Da_Immunization_Follow-up_Booster |  | 2 | 2020-11-23
63 | 07Aa_Booking-Immunization_School |  | 1 | 2020-11-23
64 | 07Ea_Medical_Doctor Consult |  | 2 | 2020-11-24
65 | 07Aa_Booking-Immunization_School |  | 1 | 2020-11-24
65 | 07Fa_Booking-Corporate |  | 5 | 2020-11-24
66 | 07Fa_Booking-Corporate |  | 1 | 2020-11-24
67 | 08Aa_National_Network |  | 2 | 2020-11-24
68 | 08Ab_National_Network_Add_Company |  | 4 | 2020-11-24
69 | 08Ab_National_Network_Add_Company |  | 4 | 2020-11-24
70 | 08Ac_National_Network_Company_Detail |  | 3 | 2020-11-24
71 | 08Ac_National_Network_Company_Detail |  | 2 | 2020-11-24
72 | 08Ae_National_Network_Employee_View |  | 5 | 24/25-11-2020
73 | 08Aa_National_Network |  | 2 | 2020-11-25
74 | 09Aa_Manage Contraindications |  | 2 | 2020-11-25
75 | 09Ab_Contraindications Add / Edit |  | 2 | 2020-11-25
76 | 09Ac_Contraindications-View |  | 1 | 2020-11-25
77 | 09Ba_Manage Manufacturer |  | 2 | 2020-11-25
78 | 09Bb_Manufacturer - Add Edit |  | 3 | 2020-11-25
79 | 09Bc_Manufacturer - Detail |  | 3 | 2020-11-25
80 | 09Ca_Manage Products |  | 2 | 2020-11-25
81 | 09Cb_Products - Add Edit |  | 3 | 2020-11-25
82 | 09Cc_Products - Detail |  | 5 | 2020-11-25
83 | 09Da_Maintenance Supplier |  | 2 | 2020-11-26
84 | 09Db_Maintenance Supplier - Add Edit |  | 2 | 2020-11-26
85 | 09Dc_Maintenance Supplier - Detail |  | 1 | 2020-11-26
86 | 10Aa_Calendar-List |  | 5 | 2020-11-26
87 | Add-Appointments |  | 3 | 2020-11-26
88 | 10Aa_Manage Roles and Rights |  | 3 | 2020-11-26
89 | 10Ab_Manage Roles and Rights |  | 3 | 2020-11-26
90 | 10Ba_Manage Staff |  | 2 | 2020-11-26
91 | 10Bb_Staff - Add Edit |  | 4 | 2020-11-26
92 | 10Bc_Staff - Add Edit |  | 4 | 2020-11-27
93 | 10Bd_Staff - Add Edit |  | 4 | 2020-11-27
94 | 10Be_Staff - Add Edit |  | 4 | 2020-11-27
95 | 10Ca_Manage Clinic |  | 2 | 2020-11-27
96 | 10Cb_Clinic - Add Edit |  | 4 | 2020-11-27
97 | 10Cc_Clinic - Details |  | 4 | 2020-11-27
98 | 10Db_Holiday list |  | 3 | 2020-11-27
99 | 10Dc_Holiday - Add Edit |  | 1 | 2020-11-27
100 | 10Ea_Manage Country |  | 2 | 2020-11-30
101 | 10Eb_Country - Add Edit |  | 2 | 2020-11-30
102 | 10Ec_Country - Detail |  | 2 | 2020-11-30
103 | 11Aa_Email - Email Layouts |  | 2 | 2020-11-30
104 | 11Ab_Edit - Email Layouts |  | 5 | 2020-11-30
105 | 12Aa_Chat |  | 8 | 2020-11-30
106 | 13Aa_Medical Information |  | 2 | 2020-11-30
107 | 13Ab_Medical Information - Detail |  | 3 | 2020-11-30
108 | 14Aa_Manage HL7 Depencies for HL7 Message |  | 4 | 2020-11-30
109 | 14Ab_HL7 Depencies Edit |  | 3 | 2020-12-01
110 | 14Ac_HL7 Depencies Detail |  | 2 | 2020-12-01
111 | 14Ba_Manage HL7 Identifiers |  | 2 | 2020-12-01
112 | 14Bb_HL7 Identifiers Edit |  | 1 | 2020-12-01
113 | 14Bc_HL7 Identifiers Detail |  | 1 | 2020-12-01
114 | 15Aa_Corporate - Manage Users |  | 2 | 2020-12-01
115 | 15Ab_Users Add Edit |  | 4 | 2020-12-01
116 | 15Ac_Users Detail |  | 3 | 2020-12-01
117 | 15Ba_Corporate - Invoice |  | 2 | 2020-12-01
118 | 15Bb_Invoice - Detail |  | 5 | 2020-12-01
119 | 15Ca_Corporate - Reports |  | 2 | 2020-12-02
120 | 16Aa_Reports - |  | 2 | 2020-12-02
121 | 17Aa_Manage-Vaccination |  | 3 | 2020-12-02
122 | 17Ab_Add/Edit-Vaccines |  | 3 | 2020-12-02
123 | frame6 |  | 2 | 2020-12-02
| COMPLETITION DATE |  |  | 2020-12-02